Chanukah Task Lists

Prioritization Key: 1=must happen today 2=could happen tomorrow, much better if it happens today 3=important, not urgent 4=can wait 5=does’nt belong on this list

Inspiration Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Begin day with Shiurim, avoid head on sefer on couch... |  |  |  |  |
|  | Learn Chanukah related Sichos and Mamorim of the Rebbe |  |  |  |  |
|  | Watch Hadlokas Neiros by the Rebbe |  |  |  |  |
|  | Listen to Sicha about Chanukah Mivtzoim/Chanukah live |  |  |  |  |
|  | Send Tzetel listing all chanukah Peulos for Brocha |  |  |  |  |
|  | Send post Chanukah Duch with report |  |  |  |  |

Public Menorah Lighting Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Choose date and location | 6 weeks ahead |  |  |  |
|  | Apply for permit |  |  |  |  |
|  | Get corporate sponsors |  |  |  |  |
|  | get some more corporate sponsors |  |  |  |  |
|  | Purchase Menorah | 6 weeks ahead |  |  |  |
|  | Set up menorah and secure from wind | 6 weeks ahead |  |  |  |
|  | set up spot lights | 1 month ahead |  |  |  |
|  | hang sign on menorah/make sign to hang | 1 month ahead |  |  |  |
|  | buy bulbs and extension cords | 6 weeks ahead |  |  |  |
|  | decide on flame for public lighting and purchase supplies |  |  |  |  |
|  | cherry picker for tall menorah |  |  |  |  |
|  | Prep your greetings message |  |  |  |  |
|  | Invite dignitary |  |  |  |  |
|  | Confirm Dignitary |  |  |  |  |
|  | Get proper title, pronunciation of name and bio for introduction |  |  |  |  |
|  | Send dignitary sample of chanukah remarks |  |  |  |  |
|  | Have back up plan for dignitary “no show” |  |  |  |  |
|  | Print brochos on handy card with transliteration. |  |  |  |  |
|  | Photographer - hire or volunteer |  |  |  |  |
|  | Videographer - hire or volunteer |  |  |  |  |
|  | Create photo op with dignitary |  |  |  |  |
|  | Plan entertainment |  |  |  |  |
|  | volunteers to help run the event |  |  |  |  |
|  | plan and purchse food |  |  |  |  |
|  | plan and purchase crafts and other station for children |  |  |  |  |
|  | Mivtzoim table, menorahs, yarmulkas, coins & pushka, guides... |  |  |  |  |
|  | Prepare numerous really short inspirational one-liners to share as you work the crowd |  |  |  |  |
|  | pick up nickels and hand out “gelt” to the children |  |  |  |  |
|  | Create RSVP form on website | 1 month ahead |  |  |  |
|  | Create a donation link | 1 months ahead |  |  |  |
|  | Design email campaign | 6 weeks ahead |  |  |  |
|  | Schedule email sequence | 1 month ahead |  |  |  |
|  | List of personal phone calls | 1 month ahead |  |  |  |
|  | Social Networking | 2 weeks ahead |  |  |  |

Chanukah at the Mall Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Choose date |  |  |  |  |
|  | Speak with Shluchim who have successfuly worked with Malls in the past to learn best practices |  |  |  |  |
|  | Contact the Mall Spacial events coordinater | 3-4 months ahead |  |  |  |
|  | reserve date, sign contract, get insurance waiver for event | 3-4 months ahead |  |  |  |
|  | Submit floor plan and how many tables and chairs needed |  |  |  |  |
|  | Can you use Mall sound system? |  |  |  |  |
|  | choose event attraction - specialty menorah (let me know when you make a sushi menorah) | 2 months ahead |  |  |  |
|  | Draw up minute to minute plan for event | 1 month ahead |  |  |  |
|  | Make supply list for all booths and activites |  |  |  |  |
|  | Purchase all supplies |  |  |  |  |
|  | welcome table with chanuka supplies and program schedule | 1 month ahead |  |  |  |
|  | sign in sheet/raffle to capture new contacts | 1 month ahead |  |  |  |
|  | use Mall wifi and have participants add their name and contact info into your website using your ipad or similar toy |  |  |  |  |
|  | Side note... The difference between the Men and the Boys...is the Price of the Toys :) |  |  |  |  |
|  | Videographer - hire or volunteer | 1 month ahead |  |  |  |
|  | Photographer - hire or volunteer | 2-3 months ahead |  |  |  |
|  | greetings | 1 week ahead |  |  |  |

Menorah Parade Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | choose a date for the parade |  |  |  |  |
|  | file for permit from police | 1 week ahead |  |  |  |
|  | arrange for parade escourt |  |  |  |  |
|  | plan parade route | 1 week ahead |  |  |  |
|  | print copies of route for parade participants |  |  |  |  |
|  | print intsructions for drivers...keep hazards on...drive through the red lights.. |  |  |  |  |
|  | order chanukah car flags | 1 week ahead |  |  |  |
|  | order car menorahs | 1 week ahead |  |  |  |
|  | Pre sell car menorahs |  |  |  |  |
|  | Pre rent car Menorahs |  |  |  |  |
|  | rent tank to lead parade | 1 week ahead |  |  |  |
|  | brochures and menorahs to hand out on parade |  |  |  |  |
|  | rent stretch hummer or other sport vehicle for excitement | 2 days ahead |  |  |  |
|  | speakers and music for lead car |  |  |  |  |
|  | designate location for starting parade and cars to get in line |  |  |  |  |
|  | Ensure space for parking at destination |  |  |  |  |
|  | Plan entertainment for destination |  |  |  |  |
|  | Alternative: plan stops along the route ie:nearby chabad house and hand out snacks to the parading cars |  |  |  |  |
|  | videographer in lead car |  |  |  |  |
|  | photographer to shot the parade |  |  |  |  |
|  | send press release |  |  |  |  |
|  | music and sound system for entertainment at destination |  |  |  |  |
|  | source of electricity for outdoor entertainment |  |  |  |  |
|  | post photos on website |  |  |  |  |
|  | write report to be included in Chanukah Duch |  |  |  |  |

Mivtzoim/Bikurei Bayis Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Arange Bochurim for Chanukah |  |  |  |  |
|  | Take care of travel and rental car |  |  |  |  |
|  | Order Mivtzoim Menorah kits | 2 weeks |  |  |  |
|  | arrange for volunteers/bochurim to pack the kits |  |  |  |  |
|  | pack mivtzoim boxes - menorah, candles, dreidel, tzedaka and guides | 2 weeks |  |  |  |
|  | Plan Mivtzoim locations for each night | 2 weeks |  |  |  |
|  | hand out hot latkes for street mivtzoim |  |  |  |  |
|  | get latkes donated by supermarket |  |  |  |  |
|  | plan which homes to visit for bikurei bayis |  |  |  |  |
|  | print map and directions or use gps |  |  |  |  |
|  | Print report form to keep track of the specific Mivtzoim details |  |  |  |  |
|  | Send camera for photo oportunities |  |  |  |  |
|  | follow up with new leads |  |  |  |  |

Parties with BB Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Review BB list and decide who you will invite when | 1 month |  |  |  |
|  | Call/email to invite | 1 week |  |  |  |
|  | follow up for rsvp | 1 month |  |  |  |
|  | Ask BB to prepare short vort to share, send link to chabad.org/chanukah |  |  |  |  |
|  | Find out BB favorite wine and desert |  |  |  |  |
|  | plan evening menu and low key festive program | 2-3 weeks |  |  |  |
|  | Plan for your children to play an active role |  |  |  |  |
|  | Ask wife to make a list of everything that needs to be purchased |  |  |  |  |
|  | go shopping |  |  |  |  |
|  | set up for party |  |  |  |  |
|  | thank wife for hosting | 1 month |  |  |  |
|  | thank wife again |  |  |  |  |
|  | prepare vort on chanukah inspiration | 1 week |  |  |  |
|  | keep credit card swipe handy for spontaneus donation urges | 1 week |  |  |  |
|  | take photo by menorah and email to BB that night |  |  |  |  |
|  | upload photo to https://www.sendoutcards.com and send with warm note |  |  |  |  |
|  | clean up, eat left overs |  |  |  |  |
|  | Shmooze with wife about the party |  |  |  |  |
|  | write report to be included in Chanukah Duch |  |  |  |  |

Personal Tasks

| Prioritize | Task | Date | Who | Completed | Moved forward |
| --- | --- | --- | --- | --- | --- |
|  | Find Menorah | 10 minutes before |  |  |  |
|  | Polish Menorah |  |  |  |  |
|  | buy oil, wicks, shamoshim |  |  |  |  |
|  | set up table for menorah |  |  |  |  |
|  | take out cash for chanukah gelt |  |  |  |  |
|  | taste test the donughts |  |  |  |  |